## Quick Project Health Check
Quick Project Health Check
Use this worksheet to assess the health of an active process improvement initiative at any stage of the project lifecycle. The intent is to provide the sponsor and project manager a tool to quickly identify major components of the effort that may need closer review. Issues addressed early save time and resources.
Project Name:
Reviewed By:
Status Scoring: Score each item as 3 - Green (On Track), 2 - Yellow (Needs Attention), or 1 - Red (At Risk).
Categories & Metrics | Score | Assessor Notes/Comments/Action Items
1. Problem, Metrics, and Scope
"Current State" Documented: The "current state" problem is documented and agreed upon by stakeholders Not just observed — has it been validated and signed off? Are there differing opinions that need resolution?
Clear Project Goal: Project goal is written in one clear sentence, using plain language, no jargon — could it be given to a new team member and have them understand it immediately?
Metric(s) Defined: Is there a clear, quantifiable baseline metric currently measured? (e.g., "Current processing time is 4 days; target is 1 day") Without a baseline, you cannot prove improvement — confirm data goes back far enough to be meaningful.
Realistic Project Size: Is the improvement focused on a single process or sub-process (not org-wide)? Narrower scope typically means faster wins and clearer attribution — flag if overly broad.
Bottleneck Pinpointed: Has the exact constraint or bottleneck in the process been mapped and agreed upon by the team doing the work?
Scope Boundaries: Are project boundaries of the targeted process clearly defined to prevent scope creep? Are they documented and readily available to stakeholders and team members?
Timelines: Are project timelines realistic and communicated to all involved parties? Are milestones visible and agreed upon? Have delays been acknowledged and rescheduled honestly?
2. Solution Design & Usability
Process Flow Mapped: Is there a visual "To-Be" process map or simple step-by-step document that anyone can follow?
Friction Check: Does the new process actually reduce effort for front-line operators, or does it just shift work onto someone else?
Exception Handling: Is there an explicit rule for how edge cases/exceptions are handled outside the main workflow?
Tool Readiness: Are any required new tools, software features, or templates built and tested? Have these been included in the project budget?
3. Stakeholder Alignment & Change Management
Sponsor Support: Has a project sponsor who can remove roadblocks been identified and is that person actively engaged? Is the functional leader/manager actively backing the change and communicating its importance?
Front-line Buy-in: Have the staff who regularly perform the affected process given input and validated that the new "future state" design is practical? Is there a clear picture of what success looks like — process, people, performance, and experience?
Status Communication: Has a project status communication cadence been established (who gets updates, how often), and is it actually happening?
Resource Availability: Do team members assigned to the project have the necessary availability in their schedule to minimize conflicting priorities and working extra hours?
Feedback Channel: Is there an easy way for operators to report issues or friction during the transition period?
4. Risks & Blockers
Risks Documented: Does a risk log exist? A simple list with likelihood and impact ratings is sufficient — the goal is visibility, not perfection.
Risks Assigned: Do all the high impact and/or high probability risks have owners and mitigation steps identified?
Critical Blockers: Are there any critical blockers preventing the next phase of work? If blockers exist, have they been escalated? Blockers that linger more than two weeks need sponsor attention.
5. Rollout & Control Mechanisms
Training Plan: Is there a training plan in place for all impacted team members? Has all necessary training and reference material been developed?
Pilot/Soft Launch: Is the new process being tested on a small sample or single team before full deployment? Correcting flows and flaws is much simpler when the number of people involved in the launch is small.
Sustainment Checks: Are daily/weekly audit checks scheduled to verify the team is following the new process rather than reverting to old habits?
Success Indicator: Is there a simple scoreboard or dashboard tracking if the target outcome is being met post-launch?
📋 Rapid Health Triage
Condition | Recommended Action
Any Red in Section 1 (Problem, Metrics, and Scope) | Stop. If you don't know where you're going and when you're supposed to get there, you're building on a foundation of sand. This phase is critical to everything that follows.
Any Red in Section 2 (Solution Design & Usability) | Pause. If the solution doesn't effectively address the issue, then the project will be a waste of time and money. Take time to review the proposed "future state" solution and ensure it is aligned with your goals.
Any Red in Section 3 (Stakeholders & Change Management) | Stop. Process changes fail when people resist them. Resolve buy-in before pushing significant workflow and/or technical changes.
Any Red or Yellow in Section 4 (Risks & Blockers) | Pause. Don't get blindsided by risks that could have been easily identified and mitigated.
Any Red or Yellow in Section 5 (Rollout) | Pause. Define audit routines and feedback channels now so habits don't slip after launch.